## Sheet1
P.O. Ref.: ASL/DA1P/PCI/R/DA1P/0213/20/4009/4002 dated 27.04.2021
SCHEDULE PLAN
Sl. No. | Particulars | Duration | Date
ESS testing at ASL after Delivery
1 | Delivery Date as per P.O. |  | 26.12.2021
2 | Targetted date for Delivery |  | 26.11.2021
3 | Despatch date |  | 24.11.2021
4 | Packing |  | 23.11.2021
5 | Pre Despatch Inspection ASL R&QA |  | 16.11.2021
6 | Final Assembly of the units |  | 11.11.2021
7 | QC Inspection / Functional Testing |  | 06.11.2021
8 | OS Loading and Internal Testing |  | 25.10.2021
9 | CPCI Launch Computer Assembly |  | 20.10.2021
10 | KVM Assembly and Wiring |  | 23.10.2021
11 | Procurement to be completed by |  | 20.10.2021
12 | Paint Filling for Engraving details |  | 15.10.2021
13 | Engraving |  | 13.10.2021
14 | Painting / Powder Coating |  | 12.10.2021
15 | Rework |  | 10.10.2021
16 | Assembly Inspection |  | 1.10.2021
17 | Fabrication Inspection |  | 20.09.2021
18 | Fabrication |  | 10.09.2021
19 | Fabrication Design Drawings |  | 01.09.2021
20 | Mechanical Design & Approval
21 | Documentation and Approval