## Sheet1
P.O. Ref.: ASL/DA1P/PCI/R/DA1P/0213/20/4009/4002 Dated 27.04.2021
1 No.Of Proto Type Unit Schedule For cPCI Launching Computer
Sl. No | Particulars | Date | Remarks
1 | Mechaniacl Chassis & items | 2021-08-01 | To be ready one no of all mechanical items for Assembling
2 | Procurement | 2021-08-01 | To be ready one no of all electrical items for Assembling
3 | Assembling & Wiring | 2021-08-16 | To be ready for Functional Test
4 | Datasol QC inspection & Functional Test | 2021-08-17
5 | Demo at ASL | 2021-08-23
6 | Rework/modification as suggested by customer |  | This will be implemented on production units
7 | Approvel for proto type unit | 2021-08-31
Schedule Plane For cPCI Launching Computer
Sl. No | Particulars | Target Date | Remarks | Responsible Person
1 | BOM Approval | 2021-07-10 |  | Purushotham Reddy
2 | ATP Approval | 2021-08-31 |  | Purushotham Reddy
3 | QTP Approval | 2021-08-31 |  | Purushotham Reddy
4 | Mechanical Design Approval | 2021-08-31 |  | Parthiban
5 | Fabrication Design Drawings | 2021-09-01 |  | Parthiban
6 | Fabrication | 2021-09-10 |  | Sridhar
7 | Fabrication Inspection | 2021-09-20 |  | Sabitha
8 | Assembly Inspection | 2021-10-01 |  | Babu Mohan
9 | Mechanical Rework if any | 2021-10-10 |  | Parthiban / Sridhar
10 | Painting / Powder Coating | 2021-10-12 |  | Parthiban / Sridhar
11 | Engraving | 2021-10-13 |  | Parthiban / Sridhar
12 | Paint Filling for Engraving details | 2021-10-15 | To be ready all Mechanical items for assembling | Parthiban / Sridhar
13 | Procurement to be completed by | 2021-10-30 | To be ready all Electrical items for assembling | Sridhar
14 | CPCI Launch Computer Assembly | 2021-11-04 | We should have all assembled unit | Babu Mohan
15 | KVM Assembly and Wiring | 2021-11-04 | We should have all assembled unit | Babu Mohan
16 | OS Loading and Internal Testing | 2021-11-11 |  | Purushotham Reddy
18 | QC Inspection / Functional Testing | 2021-11-15 |  | Sabitha / Purushotham
19 | Final Assembly of the units | 2021-11-18 |  | Babu Mohan
20 | Packing | 2021-11-23
21 | Dispatch date | 2021-11-24
22 | Targetted date to reach the customer | 2021-11-26
23 | QC Inspection / Functional Testing at RCI | 2021-12-04
24 | ESS | 2nd Week of Dec | Based on QC clearance & slots availability At ASL